## BoQ (hidden)
Tender Inviting Authority: COMMISSIONER KAYALPATTINAM MUNICIPALITY | [7 empty] | 1
Name of Work: PROVIDING WATER SUPPLY IMPROVEMENT SCHEME TO KAYALPATTANAM MUNICIPALITY IN THOOTHUKUDI DISTRICT
Contract No: 250/2010/A3
Bidder Name :
SCHEDULE OF WORKS (This BOQ template must not be modified/replaced by the bidder and the same should be uploaded after filling the relevant coulmns, else the bidder is liable to be rejected for this tender. Bidders are allowed to enter the Bidder Name and Values only)
Sl. No. | Description of work | No.or Qty. | Unit | Estimated Rate (in. Rs.) | RATE In Figures To be entered by the Bidder Rs. P |  | AMOUNT Rs. P
[5 empty] | Figures | Words
1 | Bill No..1 Construction of Infiltration well (4.5.m & 9m depth) 6 nos including pumping machinery and laying, pipe from well to sump at Ponnankurichi head works
1 | Earth work excavation above water level in light or sandy or clay soils for infiltration well of 4.5m dia (Internal) including levelling the site and as directed by the departmental officers open well excavation for infiltration well for first depth of 1m. | 192.92 | 1 m3 D57(One Cubic metre) |  | 0 | Rupees only | 0
2 | Sinking well below water level including all incidental Charges using special tools and plants such as air compressor, helmet etc., complete and including bailing out water.
1 | For 4.50 metre dia (internal)
1 | First depth of 2 metres | 12 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
2 | Second depth of 2 metres | 12 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
3 | Third depth of 2 metres | 12 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
4 | Fourth depth of 1 metres | 12 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
3 | Reinforced Cement Concrete of M30 grade (Design mix) using machine crushed hard broken granite stone jelly 20 mm for RCC works in all types of foundations, floor slabs of all shapes (Excluding cost of providing centering & fabrication of reinforcement which shall be measured & paid under separate items) including curing, complying with standard specifications as directed by the Engineer | 451.26 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
4 | Porus Concrete in CC 1:4 (one cement and four had broken granite jelly of size 20mm) for steining of infiltration wells excluding cost of centering but including curing etc, complete and as directed by the Engineer. | 251.8 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
5 | Supplying, fabricating and laying in position MS rounds or RTS rods for RCC works including cost of reinforcement, binding wire, cutting bending, cranking and tying in position with binding wire assembly, etc. | 54152 | 1kg (One kilo gram) |  | 0 | Rupees only | 0
6 | Supply and erection of steel sheet centering for all RCC works including strutting up to 3.30m height using MS sheet of size 90cmx60cm - 13 G to 10G thick welded with 25mmx25mmx6mm MS angles supported with country wood scantling of size 10cmx6.5cm at 50cm c/c strutting with casurina props of 10 cm to 13 cm dia spaced at about 90cm c/c as directed by the Engineer.
1 | a). Plane surface | 137.41 | 1 m2 (One Square metre) |  | 0 | Rupees only | 0
2 | b). Square column | 486 | 1 m2 (One Square metre) |  | 0 | Rupees only | 0
3 | c). Curved surface | 928.77 | 1 m2 (One Square metre) |  | 0 | Rupees only | 0
7 | Refilling sides of Infiltration wells with excavated sand etc. all complete as per standard specifications and as directed by the Engineer. | 186.14 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
8 | Supplying and fixing of PVC encapsulated CI steps for access the intake well including fixing charges complying with standard specification and as directed by the Engineer etc. | 70 | 1 Each (one each) |  | 0 | Rupees only | 0
9 | Supply, delivery and fixing of FRC Manhole frame and cover of size of 0.6 x 0.6m with light duty cover etc, complete as per standard specifications and as directed by the Engineer | 12 | 1 Each (one each) |  | 0 | Rupees only | 0
10 | Providing cutting edges for infiltration well using 2G MS Plate including all cost and conveyance of all materials etc, complete as per standard specifications and as directed by the Engineer | 1435.5 | 1kg (One kilo gram) |  | 0 | Rupees only | 0
2 | MECHANICAL WORKS
1 | Supply, delivery and installation of Open well submersible pumpset confirming to ISI Mark IS:14220 with Bronze impellors, S.S.Shaft etc., as per special specification for pumping water from Infiltration well to Sump located in the river bank at an average distance of 100 m for 6 wells (6 working + 6 standby). 10 m submersible cable needs to be supplied along with Pump.1250 lpmx40m head | 12 | 1 Each (one each) |  | 0 | Rupees only | 0
2 | Labour Charges for erection of Horizontal shaft, centrifugal pumpset (Coupled/Monoblock) in bore well/Open well including fixing of suction pipe and foot valve upto a maximum depth of 7 metres and delivery pipes to the required length with valves, pressure gauges upto the exterior wall of pump room and erection of panel Board consisting of TPIC switches starter, voltmeter, Ammeter, Capacitor single phasing preventor and laying and jointing the cables and twin earthing as per IE rules including providing bed blocks etc., complete and operating the pumps and trial run for 10 days including signing of completion of reports as required by EB authorities. | 12 | 1 Each (one each) |  | 0 | Rupees only | 0
3 | LAYING OF DI SS PIPE FROM INFILTRATION WELLS TO SUMP
1 | Earthwork excavation and depositing on bank with an initial lead of 10m and initial lift of 2m in trenches in Hard stiff clay, stiff black cotton, hard red earth, shales, murram gravel, stoney earth and earth mixed with small boulders and hard gravelly soil all complete as per standard specifications and as directed by the Engineer
1 | 150mm dia DI SS pipes | 3600 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
2 | Supplying and conveying of following sizes of DI pipes S / S (K7 class) to site, confirming to specification as per IS:8329-2000 for standard length including cost of pipes, testing charges at factory, labour charges for loading, unloading and stacking at site etc. complete as per standard specifications and as directed by the Engineer. |  |  |  | 0 | Rupees only | 0
1 | 150mm dia DI SS pipes | 3600 | 1 Rm (One Running Metre) |  | 0 |  | 0
3 | Lowering of DI Pipes (K7 Class) and specials carefully into the trench and laying to proper grade and alignment including labour charges, incidental and operational charges etc complete as per standard specifications and as directed by the Engineer | [5 empty] | 0
1 | 150mm dia DI SS pipes | 3600 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
4 | Jointing the K7 DI pipes and specials with Socket & Spigot ends (tyton rubber joints) including cost of jointing materials such as lubricants, rubber gaskets and testing to the required pressure including conveyance of water for filling during testing, labor charges and all other incidental charges etc., complete as per standard specifications and as directed by the Engineer.
1 | 150mm dia DI SS pipes | 120 | 1 Each (one each) |  | 0 | Rupees only | 0
5 | Cutting of DI pipes and specials true to axis and filing smoothly and finishing the ends complete, with / without water in the pipe including labour charges, incidental and operational charges etc complete as per standard specifications and as directed by the Engineer .
1 | 150mm dia DI SS pipes | 20 | 1 Each (one each) |  | 0 | Rupees only | 0
6 | Refilling trenches with excavated soil in layers not exceeding 20 cm in depth, ramming and consolidation of each layer, watering etc. all complete as per standard specifications and as directed by the Departmental Engineer.
1 | 150mm dia pipe | 3600 | 2 Rm (One Running Metre) |  | 0 | Rupees only | 0
4 | PIPING ARRANGEMENTS AT INFILTRATION WELL AND SUMP
1 | Supplying and conveying of the following DI D/F pipes and Specials, confirming to specification as per IS:8329-2000 including loading, unloading, transportation and stacking at site etc. complete as per standard specifications as directed by the Engineer
1 | 150mm dia CI pipe | 60 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
2 | Laying of Pipes | 60 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
3 | Jointing of 150 mm DI duck foot bend | 48 | 1 Each (one each) |  | 0 | Rupees only | 0
4 | 150 mm DI duck foot bend, 150 mm dia DI DF 90° bend, 150x0.90m DI Fld spt tail piece | 3120 | 1kg(One kilo gram) |  | 0 | Rupees only | 0
5 | ELECTRICAL WORKS
1 | Supply and delivery of Auto transformer starter (Fully Automatic Air Break) for operating the submersible pumpsets from control room confirming to IS 13947. (6 working + 6 standby). | 12 | 1 Each (one each) |  | 0 | Rupees only | 0
2 | Supply and delivery of 3 Core/50Sq.mm/ 1.1 KV grade Armoured Aluminium conductor cable conforming to IS 1554, Part-I with ISI marking suitable for laying in ground connecting common control room and sub motors erected in infiltration wells located at a distance of 500 m from Bank. | 15000 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
3 | Laying the above cable in ground connecting Isolator of Infiltration wells and panel board to be erected in control room with necessary anchoring arrangements. | 14400 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
4 | For Pump set Errection GI Specials
1 | 100 mm GI Pipe | 36 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
2 | 100 mm GI Tee | 12 | 1 Each (one each) |  | 0 | Rupees only | 0
3 | 100 mm GI Bend | 12 | 1 Each (one each) |  | 0 | Rupees only | 0
4 | 100 mm GM Gate Valve | 12 | 1 Each (one each) |  | 0 | Rupees only | 0
5 | 100 mm GM NRV | 12 | 1 Each (one each) |  | 0 | Rupees only | 0
6 | 100 mm GM Flange set | 24 | 1 Each (one each) |  | 0 | Rupees only | 0
7 | 40mm GI Pipe for cable | 3600 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
8 | 40mm GI Bend | 48 | 1 Each (one each) |  | 0 | Rupees only | 0
5 | Angarange Arrangements | 738 |  |  | 0 | Rupees only | 0
1 | No.2 Proposed Construction of 2 LL Capacity sump at Ponnankurichi Head works
1 | Open well foundation for Earthwork - excavating and depositing on sides with an initial lead of 10m and initial lift of 2m in trenches (Hard stiff clay, stiff black cotton, hard red earth, shales, murram gravel, stoney earth and earth mixed with small boulders and hard gravelly soil) including shoring, strutting and bailing out water wherever necessary etc complete as per standard specifications and as directed by the Engineer
1 | Upto 2m depth | 168.24 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
2 | From 2m depth to 4.2 m depth | 185.06 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
2 | Cement concrete 1:4:8 using 40 mm gauge hard broken stone jelly for Plain Cement Concrete works including laying in layers of not more than 15 cm thick including ramming, curing, etc. complete. | 16.82 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
3 | Reinforced Cement concrete M30 (Design mix) using 20mm gauge hard broken stone jelly for reinforced cement concrete works excluding cost centering, shuttering and cost of steel reinforcement but including laying in position, compacting, curing, finishing, etc. complete. | 65.43 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
4 | Providing & fabricating steel reinforcement for RCC works including decoiling, cutting, hooking, bending, cranking fabricating to required shape placing in position and binding complete including cost of binding wire, all RCC works like foundations, roof slab etc. complete as per standard specifications and as directed by the Engineer | 7851 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
5 | Providing rigid and water tight centering and shuttering using best quality of wooden planks / ply wood sheets / steel centering sheets including strutting etc., complete all for RCC items fixed in position as required including labour for careful removal of form work etc., complete as per specifications and as directed by the Engineer.
1 | Roof slab | 70.12 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
2 | Outer area of side wall - 0-3m | 93.76 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
3 | Outer area of side wall - 3-4m | 20.31 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
4 | Inner area of side wall - 0-3m | 93.76 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
5 | Inner area of side wall - 3-4m | 20.31 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
6 | Side of roof slab | 4.69 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
6 | Supply, delivery and fixing of RCC Ventilator on the top of cover slab with wire mesh cover etc complete as per standard specifications and as directed by the Engineer | 4 | 1 Each (one each) |  | 0 | Rupees only | 0
7 | Refilling sides of underground sump with excavated soil in layers not exceeding 20cm in depth, ramming and consolidation of each layer, watering etc. all complete as per standard specifications and as directed by the Engineer. | 6.38 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
8 | Transportation of excess earth from the site, including labour charges and transport to 1km from the site as per standard specifications and as directed by the Engineer | 161.86 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
9 | Supply, delivery and fixing of Cast Iron Manhole frame and cover of size 0.6 x 0.6 m with light duty cover etc complete as per standard specifications and as directed by the Engineer | 2 | 1 Each (one each) |  | 0 | Rupees only | 0
10 | Providing and fixing in position of Mild Steel (MS) ladder of 3.50m height, 0.5m width and 80mm thick hand rails including all necessary permanent fittings etc, complete as per standard specifications and as directed by the Engineer | 2 | 1 Each (one each) |  | 0 | Rupees only | 0
2 | PIPING ARRANGEMENTS
1 | Earthwork - excavating and depositing on sides with an initial lead of 10m and initial lift of 2m in trenches (Hard stiff clay, stiff black cotton, hard red earth, shales, murram gravel, stoney earth and earth mixed with small boulders and hard gravelly soil) including shoring, strutting and bailing out water wherever necessary etc complete as per standard specifications and as directed by the Engineer for laying of pipes
1 | Suction pipe (200 mm DI) | 16 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
2 | Supplying and conveying of following sizes of DI pipes S / S (K7 class) to site, confirming to specification as per IS:8329-2000 for standard length including cost of pipes, testing charges at factory, labour charges for loading, unloading and stacking at site etc. complete as per standard specifications and as directed by the Engineer - 200 mm dia pipe
1 | Suction pipe (200 mm DI) | 16 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
3 | Lowering, laying and jointing of DI pipes (K7 Class) and specials with socket & spigot ends (tyton rubber joints), lowering carefully into the trench and laying to proper grade and alignment including cost of jointing materials such as rubber gaskets, testing to the required pressure including conveyance of water for filling during testing, labour charges, incidental and operational charges etc., complete as per standard specifications and as directed by the Engineer.
1 | Suction pipe (200 mm DI) | 16 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
4 | Refilling the excavated trenches using excavated earth including complete consolidation and leveling as per standard specifications and as directed by the Engineer | 16 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
5 | Supplying and Conveying of following CI Double Flanged Sluice Valves (PN 1.0) with cap of following sizes confirming to IS:14846, to site, including flanged tail pieces and other specials as required, loading, unloading, transportation charges & stacking at site etc. complete per specifications and as directed by the Engineer.
1 | Suction pipe (200 mm DI) | 4 | 1 Each (one each) |  | 0 | Rupees only | 0
2 | Delivery pipe (200mm DI) | 4 | 1 Each (one each) |  | 0 | Rupees only | 0
3 | MECHANICAL WORKS
1 | Supply, delivery and installation of horizontal split casing Centrifugal pump (1500 RPM) confirming to ISI Mark with Bronze impellors and S.S.410 Shaft etc., as per special specification for pumping water from Sump to OHT's located in Kayalpatnam Town. (2 working + 2 standby).
1 | 2500 lpm @ 100 m head | 4 | 1 Each (one each) |  | 0 | Rupees only | 0
2 | Installation Charges Labour Charges for erection of Horizontal shaft, centrifugal pumpset (Coupled/Monoblock) in bore well/Open well including fixing of suction pipe and foot valve upto a maximum depth of 7 metres and delivery pipes to the required length with valves, pressure gauges upto the exterior wall of pump room and erection of panel Board consisting of TPIC switches starter, voltmeter, Ammeter, Capacitor single phasing preventor and laying and jointing the cables and twin earthing as per IE rules including providing bed blocks etc., complete and operating the pumps and trial run for 10 days including signing of completion of reports as required by EB authorities. | 4 | 1 Each (one each) |  | 0 | Rupees only | 0
2 | Supply, delivery and fixing of SS sealed Diaphragm type pressure gauge on discharge header, 100mm etc., complete as per standard specifications and as directed by the Engineer | 4 | 1 Each (one each) |  | 0 | Rupees only | 0
3 | Supply and installation at site, non-return valve suitable for water service, 200mm diameter, flanged ends with support concrete pad etc., complete as per standard specifications and as directed by the Engineer | 4 | 1 Each (one each) |  | 0 | Rupees only | 0
4 | Supply and delivery of discharge pipe of 350mm diameter of DI (K9 class), flanged ends including appurtenances etc., complete as per standard specifications and as directed by the Engineer | 80 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
5 | Supply and delivery including fixing of piping and appurtenances (Specials) such as Tee 350 x 350 x 350 (1 No.), Taper 350 x 200 (1 No.), Taper 250 x 200 (1 No.), Taper 200 x 150 (1 No.), Duct foot bend 350mm (1 No.), Short pipe 1m 350mm (1 No.) 90º bend | 5920 | 1 Kg (One Kilo Gram) |  | 0 | Rupees only | 0
4 | ELECTRICAL WORKS
1 | Supply and delivery of FCMA - soft starter for operating the pumpsets erected in sump on the bank of river | 4 | 1 Each (one each) |  | 0 | Rupees only | 0
2 | Supply and delivery of 3 1/2 Core/150 Sq.mm/ 1.1 KV grade/ Armoured Aluminium conductor cable conforming to IS 1554, Part-I with ISI marking suitable for laying in ground / air connecting EB supply point and panel board through EB Meter box. | 120 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
3 | Laying the above cable connecting EB Supply point and panel board / EB Meter Box including all cost and ocnveyance etc.complete as per standard specification | 30 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
4 | Supply, delivery and laying of all required electrical cables from control panel room to infiltration well 35 Sq mm including all cost and ocnveyance etc.complete as per standard specification | 20 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
5 | Supply and installation of earthing (grounding) arrangement for electrical equipment complete with accessories such as masonry, flat, fasteners, earth pit erection and requisite works etc., complete as per standard specifications and as directed by the Engineer | 1 | 1 Each (one each) |  | 0 | Rupees only | 0
6 | Supply and installation of Indoor and outdoor light fittings, cables, cut-out and ventilation fans complete with accessories and mounting etc., complete as per standard specifications and as directed by the Engineer | 1 | 1 Each (one each) |  | 0 | Rupees only | 0
7 | Supply and delivery of safety equipment and tools such as fire extinguisher (dry-type), first-aid box, fire bucket, rubber mat, safety rules chart, shock treatment chart and requisite materials etc., complete as per standard specifications and as directed | 1 | 1 Each (one each) |  | 0 | Rupees only | 0
8 | Supply and delivery of maintenance tools/equipment such as adjustable wrench, jaw spanner set, screw drivers, pliers, hacksaw frame etc. , complete as per standard specifications and as directed by the Engineer | 1 | 1 Each (one each) |  | 0 | Rupees only | 0
9 | Supply, delivery and erection of capacitor banks for the new centrifugal pumps at site to improve Power Factor. The capacitors shall be of mixed did-electric type and of reputed make etc., complete as per standard specifications and as direction | 1 | 1 Each (one each) 110 KVA |  | 0 | Rupees only | 0
10 | Transformer yard earthing (Upto 250 KVA transformer sub-station)etc., complete as per standard specifications and as direction | 1 | 1 Each (one each) |  | 0 | Rupees only | 0
11 | Providing Transformer sub station / dedicated powerline from TNEB pole including erection charges etc., complete as per standard specifications and as direction | 1 | 1 Each (one each) |  | 0 | Rupees only | 0
12 | Supplying, delivery and fixing of MV panel board, when the transformer sub station is within 15m from the pump room with incoming ACBs and outgoing ACBs and MCBs. (120 KW to 200 KW) etc., complete as per standard specifications and as direction | 1 | 1 Each (one each) |  | 0 | Rupees only | 0
13 | Supply, delivery and fixing of 110 KVA Generator etc., complete as per standard specifications and as direction | 1 | 1 Each (one each) |  | 0 | Rupees only | 0
1 | No.3 Proposed Pumping Main From Collection Sump to Proposed and Existing OHT
1 | Earth work excavation and depositing on bank with initial lead 10m and lift of 2.0m in the following classification of soils, bailing out water wherever necessary including providing danger lights etc., and as directed as per specification SS 20B and special specification. Hard stiff clay, stiff block cotton, hard red earth, shales, murrams, gravely stoney earth mixed with 50% small sized boulders and hard gravelly soil etc. complete as per standard specifications and as directed by the Engineer.
1 | 350 mm diameter | 27004 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
2 | 300 mm diameter | 880 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
3 | 200 mm diameter | 1758 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
4 | 150 mm diameter | 1335 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
5 | 100 mm diameter | 4503 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
2 | Supplying and conveying of following sizes of DI pipes- K9 Class to site, confirming to specification as per IS:8329-2000 for standard length including cost of pipes, testing charges at factory, labour charges for loading, unloading and stacking at site etc. complete as per standard specifications and as directed by the Engineer.
1 | 350 mm diameter | 27004 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
2 | 300 mm diameter | 880 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
3 | 200 mm diameter | 1758 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
4 | 150 mm diameter | 1335 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
5 | 100 mm diameter | 4503 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
6 | Specials | 65473 | 1 Kg (One Kilo Gram) |  | 0 | Rupees only | 0
3 | Lowering of DI Pipes (K9 Class) and specials carefully into the trench and laying to proper grade and alignment including labour charges, incidental and operational charges etc complete as per standard specifications and as directed by the Engineer
1 | 350 mm diameter | 27004 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
2 | 300 mm diameter | 880 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
3 | 200 mm diameter | 1758 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
4 | 150 mm diameter | 1335 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
5 | 100 mm diameter | 4503 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
4 | Jointing the DI pipes and specials with Socket & Spigot ends (tyton rubber joints) including cost of jointing materials such as lubricants, rubber gaskets and testing to the required pressure including conveyance of water for filling during testing, labour charges and all other incidental charges etc., complete as per standard specifications and as directed by the Engineer.
1 | 350 mm diameter | 5401 | 1 Each (one each) |  | 0 | Rupees only | 0
2 | 300 mm diameter | 176 | 1 Each (one each) |  | 0 | Rupees only | 0
3 | 200 mm diameter | 352 | 1 Each (one each) |  | 0 | Rupees only | 0
4 | 150 mm diameter | 267 | 1 Each (one each) |  | 0 | Rupees only | 0
5 | 100 mm diameter | 901 | 1 Each (one each) |  | 0 | Rupees only | 0
5 | Cutting of DI pipes and specials true to axis and finishing the ends complete, with / without water in the pipe including labour charges, incidental and operational charges etc., complete as per standard specifications and as directed by the Departmental Engineer
1 | 350 mm diameter | 108 | 1 Each (one each) |  | 0 | Rupees only | 0
2 | 300 mm diameter | 4 | 1 Each (one each) |  | 0 | Rupees only | 0
3 | 200 mm diameter | 7 | 1 Each (one each) |  | 0 | Rupees only | 0
4 | 150 mm diameter | 5 | 1 Each (one each) |  | 0 | Rupees only | 0
5 | 100 mm diameter | 18 | 1 Each (one each) |  | 0 | Rupees only | 0
6 | Labour charge for cutting open BT or Macadam roads for laying rising mains / feeder main etc complete as per standard specifications and as directed by the Engineer | 2661 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
7 | Supplying and Conveying of following CI Double Flanged Sluice Valves (PN 1.0) with cap of following sizes confirming to IS:14846, to site, including PVC flanged tail pieces and other specials as required, loading, unloading, transportation charges & stacking at site etc. complete as per standard specifications and as directed by the Engineer
1 | 350 mm diameter | 4 | 1 Each (one each) |  | 0 | Rupees only | 0
2 | 300 mm diameter | 1 | 1 Each (one each) |  | 0 | Rupees only | 0
3 | 200 mm diameter | 1 | 1 Each (one each) |  | 0 | Rupees only | 0
4 | 150 mm diameter | 1 | 1 Each (one each) |  | 0 | Rupees only | 0
5 | 100 mm diameter | 2 | 1 Each (one each) |  | 0 | Rupees only | 0
8 | Supplying and Conveying to site, for scouring purposes, CI sluice valves (PN 1.0) of following sizes confirming to IS:14846 including CI flanged tail pieces and other specials as required, loading, unloading, transportation charges and stacking, including CI bends and pipe for discharge above ground level etc complete as per standard specifications and as directed by the Engineer.
1 | 200mm diameter | 4 | 1 Each (one each) |  | 0 | Rupees only | 0
9 | Supplying and fixing Double Air Valves with the following specials including all cost and conveyance of all materials etc.complete as per standared specification |  |  |  | 0 | Rupees only | 0
1 | 80mm Double Air Valve | 7 | 1 Each (one each) |  | 0 | Rupees only | 0
10 | Construction of masonry pit for fixing as per Chief Engineer (TWAD) W.R. / memo No. TDSV / TC / DO 11 / 91 / CE / WR, dt: 30.12.91, the foundation will be in PCC 1:4:8 and brick work in cement mortar 1:5 and plastering in CM 1:5 including all cost andd conveyance etc.complete.Sluice Valve
1 | 350 mm diameter | 4 | 1 Each (one each) |  | 0 | Rupees only | 0
2 | 300 mm diameter | 1 | 1 Each (one each) |  | 0 | Rupees only | 0
3 | 200 mm diameter | 1 | 1 Each (one each) |  | 0 | Rupees only | 0
4 | 150 mm diameter | 1 | 1 Each (one each) |  | 0 | Rupees only | 0
5 | 100 mm diameter | 2 | 1 Each (one each) |  | 0 | Rupees only | 0
6 | Scour Valve - 200 mm diameter | 4 | 1 Each (one each) |  | 0 | Rupees only | 0
7 | 80mm Double Air Valve | 7 | 1 Each (one each) |  | 0 | Rupees only | 0
11 | Refilling trenches with excavated soil in layers not exceeding 20 cm in depth, ramming and consolidation of each layer, watering etc. all complete as per standard specifications and as directed by the Engineer. Total Earth work excavation
1 | Deduct for 350mm dia. pipe | 27004 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
2 | Deduct for 300mm dia. pipe | 880 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
3 | Deduct for 200mm dia. pipe | 1758 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
4 | Deduct for 150mm dia. pipe | 1335 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
5 | Deduct for 100mm dia. pipe | 4503 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
12 | Supplying & fixing Electronic water meter Connected to Converter to give a remote indication of Totalisation and Flow rate with option for computer connectivity including censor and Totaliser etc all complete. | 1 | 1 Each (one each) |  | 0 | Rupees only | 0
1 | No.4 Proposed Construction of 4 LL OHT at Arumuganeri Road at Kayalpattanam municipality |  |  |  | 0 | Rupees only | 0
1 | Earth work excavation and depositing on bank with initial lead 10m and lift of 2.0m in the following classification of soils, bailing out water wherever necessary including providing danger lights etc., and as directed as per specification SS 20B and special specification. Hard stiff clay, stiff block cotton, hard red earth, shales, murrams, gravely stoney earth mixed with 50% small sized boulders and hard gravelly soil etc. complete as per standard specifications and as directed by the Engineer.
1 | First depth of 2m | 25.16 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
2 | Second depth of 2m | 180.62 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
2 | Sand filling for foundation with river sand including consolidation ramming etc. complete as per standard specifications and as directed by the Engineer-incharge | 8.39 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
3 | Plain Cement concrete 1:4:8 (one cement, four sand and eight course aggregate of 40mm size hard blue granite broken stone) for levelling course for foundation including the cost of mixing, placing the concrete in position, consolidating finishing and curing etc., complete and as directed for works above 1.50m and upto 4.50m depth below ground level. | 8.39 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
4 | Reinforced cement concrete M30 design mix using 10mm and 20mm Hard Broken Stone. The rates excluding the cost of supplying, fabricating and placing in opposition of MS / RTS Grills for reinforcement and centering, strutting & shuttering, but including cost of mixing, placing the concrete in position, vibrating, consolidating, finishing and curing the concrete etc., complete and as directed by the Engineer-in-charge. (The rates inclusive of testing the reservoir for the water tightness of the structure) From G.L upto 4.50m depth
1 | (i) below 1.50m to 4.50m depth from G.L | 40.01 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
2 | Below G.L upto 1.50m depth | 18.64 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
3 | Above G.L upto 4.50m height | 24.93 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
4 | Above 4.50m to 7.32m ht., from G.L | 24.93 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
5 | Above 7.32m to 10.98m ht., from G.L | 14.63 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
6 | Above 10.98m to 12.00 m ht., from G.L | 15.67 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
5 | Reinforced cement concrete M30 design mix using 10mm and 20mm Hard Broken Stone. The rates excluding the cost of supplying, fabricating and placing in opposition of MS / RTS Grills for reinforcement and centering, strutting & shuttering, but including cost of mixing, placing the concrete in position, vibrating, consolidating, finishing and curing the concrete etc., complete and as directed by the Engineer-in-charge. (The rates inclusive of testing the reservoir for the water tightness of the structure)
1 | Above 10.98m to 14.64m ht., from G.L | 54.44 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
2 | Above 14.64m ht., to 18.30m ht., | 47.83 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
6 | Centering for soffits of reinforced cement concrete slabs or plain surface including strutting upto 3m ht., using MS sheet of size 90 x 60cm and BG.10 gauge stiffened with welded MS angles of size 25x 2 x 3mm laid over silver oak (country wood) joints of 10 x 6.5cm spaced at about 90cm c/c and supported by Casuarina props of 10 to 13cm dia. at 75cm c/c complying with standard specification and as directed by the Engineer-in-charge Plane surface
1 | Upto 3.30m ht., from G.L | 179.67 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
2 | From 3.30m to 4.3 m ht. | 142.47 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
3 | From 6.30m to 7.30m ht. | 142.47 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
4 | From 10.30m to 11.30m ht. | 142.47 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
5 | From 12.30m to 13.30m ht. | 115.77 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
6 | From 15.30m to 16.30m ht. | 128.12 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
7 | Centering for square column -
8 | upto 3.30m ht. | 100.8 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
9 | From 3.30m to 4.30m ht., | 15.68 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
10 | From 4.30m to 5.30m ht., | 22.4 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
11 | From 5.30m to 6.30m ht., | 22.4 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
12 | From 6.30m to 7.30m ht., | 67.68 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
13 | From 7.30m to 8.30m ht., | 11.82 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
14 | From 8.30m ht., to 9.30m ht., | 22.4 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
15 | From 9.30m ht., to 10.30m ht., | 22.4 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
16 | From 10.30m ht., to 11.30m ht., | 16.8 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
17 | From 11.30m ht., to 12.30m ht., | 22.4 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
18 | Centering for curved surface
19 | From 13.30m to 14.30m ht., | 15.87 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
20 | From 14.30m to 15.30m ht., from ground level | 83.05 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
21 | From 15.30m to 16.30m ht., | 152.22 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
22 | From 13.30m to 14.30m ht.,from ground level | 16.1 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
23 | From 15.30m to 16.30m ht.,from ground level | 69.17 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
24 | Centering for circular column
25 | up to 1.50m below GL & 3.00M above GL | 5.53 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
26 | From 3.30 to 4.30m ht., | 0.76 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
27 | From 4.3m to 5.3m ht., | 1.26 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
28 | From 5.3m to 6.3m ht., | 1.26 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
29 | From 6.3m to 7.3m ht., | 3.28 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
30 | From 7.3m to 8.3m ht., | 1.26 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
31 | From 8.3m to 9.3m ht., | 1.26 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
32 | From 9.3m to 10.3m ht., | 1.26 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
33 | From 10.3m to 11.30m ht., | 1.26 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
34 | From 11.3m to 12.30m ht., | 1.26 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
35 | From 12.3m to 13.30m ht., | 0.75 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
36 | Circular Column inside the tank
37 | From 12m to 12.30m ht. | 1.88 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
38 | From 12.30m to 13.30m ht. | 6.28 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
39 | From 13.30m to 14.30m ht. | 6.28 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
40 | From 14.30m to 15.30m ht. | 6.28 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
41 | From 15.30m to 15.45m ht. | 0.94 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
7 | Supplying, fabricating and placing in position of RTS grills for reinforcement for various members including cost of steel for all RCC works etc., complete as per standard specifications and as directed by Departmental Engineer. The rate to include the cost of binding wire also. | 24108 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
8 | Painting two coats with approved cement paint best quality over the outer wall surface including cost of cement paint etc. complete complying with standard specification etc., complete as per standard specifications and as directed by Engineer | 1788.17 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
9 | Providing Cut stone set in CM 1:3 (one cement and three sand) using well dressed cut stone supporting inlet pipe of size 0.30 x 0.30 x 0.15m for service reservoir etc., complete as per standard specifications and as directed by Engineer | 0.02 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
10 | Supplying and fixing in position of RCC 1:1½:3 (one cement, one and half sand and three blue course aggregate of 20mm size hard broken stone) inside access ladder of 0.60m width to a height of 5.50m of approved design and pattern inside the tank including cost of cement, reinforcement, centering, shuttering, strutting etc., complete as generally shown in the plan and as directed. | 2 | 1 Each (one each) |  | 0 | Rupees only | 0
11 | Construction of RCC spiral staircase in RCC 1:1.5:3 (1 Cement : 1.5 Sand : 3 Coarse Aggregate) using 20 mm HBGS of 1.80 m diameter of required height for approach to the roof of Service Reservoir with RCC Handrails including earthwork excavation, providing CC 1:4:8 mix, RCC footing 1:1.5:3 mix, GL platform etc., and also including cost of steel reinforcement, fabrication charges, scaffolding, centering, precasting charges, cement, painting etc. complete as per standard specifications and as directed by Departmental Engineer. The staircase shall be braced to the column of service reservoir at suitable interval. (in the BOQ, quantity column the exact height to be mentioned from GL to roof slab bottom to get total value of work to be done. | 1 | 1 Each (one each) |  | 0 | Rupees only | 0
12 | Supplying and fixing in position of 0.60 x 0.60m water tight CI manhole frame and cove of approved pattern at the roof slab and as directed. The manhole frame and cover should be of light duty and confirming to IS:1726-1974 | 2 | 1 Each (one each) |  | 0 | Rupees only | 0
13 | Supply and fixing in position of enamel water level indicator with all accessories of approved pattern and design etc., complete as per standard specifications and as directed by Engineer | 1 | 1 Each (one each) |  | 0 | Rupees only | 0
14 | Supplying and fixing of RCC 1:1.5:3 (1 Cement : 1.5 Sand : 3 Coarse Aggregate) using 20 mm HBGS for RCC Handrails of 0.91 m height over the top of roof slab of approved pattern and design including the cost of reinforcement, centering, precasting, finishi | 42 | 1 Rm (One Running Metre) |  | 0 | Rupees only | 0
15 | Providing and fixing of RCC 1:2:4 (one cement, two sand and four course aggregate of 20mm size hard blue granite broken stone) for ventilators of approved pattern including cost of cement, reinforcement, centering, shuttering, strutting etc., complete as | 4 | 1 Each (one each) |  | 0 | Rupees only | 0
16 | Providing lightning arrestor etc., complete as per standard specifications and as directed by Departmental Engineer | 1 | 1 Each (one each) |  | 0 | Rupees only | 0
17 | Clearing and levelling the site etc., complete as per standard specifications and as directed by Departmental Engineer | 440 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
2 | Piping Appurtenances
1 | Earth work excavation for pipe line laying work in all soils except hard rock requiring blasting, including bailing out water wherever necessary with initial lead and lift etc., complete as per standard specification
1 | For laying Specials | 8 | Running Metre |  | 0 | Rupees only | 0
2 | Supply and delivery of the Cast Iron D/F sluice valves for nominal pressure PN I with cap non-rising high tensile brass stem with valve opening wheel in anti-clockwise direction confirming to IS:14846 / 2000 PN 1 and as amended from time to time.
1 | a). 200mm dia. CI D/F sluice valve | 1 | 1 Each (one each) |  | 0 | Rupees only | 0
1 | b). 100mm dia. CI D/F sluice valve for scour | 1 | 1 Each (one each) |  | 0 | Rupees only | 0
3 | Supply & delivery of tail pieces for sluice valve
1 | 200mm F/spi tail pieces | 35 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
2 | 200mm F/soc tail pieces | 36 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
3 | 100mm F/spi tail pieces | 14 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
4 | 100mm F/soc tail pieces | 16 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
4 | Supply, delivery of CI D/F pipes and specials of various length both standard and non-standard as per IS specification No. 7181 / 86 and IS:1538 / 78 part I to XXIII and as amended from time to time including cost of loading, fright, unloading and stacking including all cost and conveyance etc.complete. Inlet connection
1 | 150mm x 2.75m CI D/F pipe | 523.5 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
2 | 150mm x 2.25m CI D/F pipe (non-standard) | 88.1 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
3 | 150mm x 1.35m CI D/F pipe (non-standard) | 38.22 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
4 | 150mm x 0.60m CI D/F pipe (non-standard) | 33.32 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
5 | 150mm x 90º Duck foot bend | 47 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
6 | 150 x 150 x 150mm CI Tee | 94 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
7 | 150mm x 0.90m CI Fld spt tail piece | 46 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
8 | 150mm x 90º D/F bend | 58 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
9 | Delivery arrangement
10 | 200mm x 2.75m CI D/F pipe | 202.75 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
11 | 200mm x 0.60m CI D/F pipe (non-standard) | 104 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
12 | 200mm x 90º Duck foot bend | 74 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
13 | 200mm CI Bell mouth | 23 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
14 | Over flow arrangement
15 | 150mm x 2.75m CI D/F pipe | 523.5 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
16 | 150mm x 1m CI D/F pipe | 46.6 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
17 | 150mm x 0.60m CI D/F pipe (non-standard) | 33.32 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
18 | 150mm x 90º Duck foot bend | 47 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
19 | 150mm CI Bell mouth | 15 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
20 | Scour arrangement
21 | 100mm x 2.75m CI D/F pipe | 453.43 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
22 | 100mm x 1.80m CI D/F pipe | 45.3 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
23 | 100mm x 1m CI D/F pipe | 28.9 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
24 | 100mm x 0.75m CI D/F pipe | 23.78 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
25 | 100mm x 0.60m CI D/F pipe | 2.7 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
26 | 100 x 100 x 100mm CI D/F Tee | 26 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
27 | 100mm x 90º Duck foot bend | 26 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
28 | 100mm CI Bell mouth | 9 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
29 | 100mm CI semi circular bend | 34 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
5 | Labour charges for lifting of pipes and specials in vertical direction and fixing in position etc., complete as per standard specifications and as directed by Engineer-in-charge
1 | 0 to 2 m | 331 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
2 | 2 to 4 m | 331 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
3 | 4 to 6 m | 331 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
4 | 6 to 8 m | 331 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
5 | 8 to 10 m | 331 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
6 | 10 to 12 m | 331 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
7 | 12 to 14 m | 331 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
8 | 14 to 16 m | 331 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
6 | Construction of masonry pit for fixing as per Chief Engineer (TWAD) W.R. / memo No. TDSV / TC / DO 11 / 91 / CE / WR, dt: 30.12.91, the foundation will be in PCC 1:4:8 and brick work in cement mortar 1:5 and plastering in CM 1:5
1 | 200mm Sluice Valve (1.50mx0.90m) | 1 | 1 Each (one each) |  | 0 | Rupees only | 0
2 | 100mm Sluice Valve (1.20x0.75) | 1 | 1 Each (one each) |  | 0 | Rupees only | 0
7 | Refilling with excavated earth in layers of 15cm thick including watering and ramming to consolidation etc., complete as per standard specification | 8 | 1 Rm (One Running metre) |  | 0 | Rupees only | 0
3 | Compound Wall
1 | Earthwork excavation in all soils for foundation except hard rock that requires blasting with initial lead of 10m and lift of 2m etc. complete as per standard specifications complete | 29.25 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
2 | Providing PCC 1:4:8, using 40mm ISS HBG metal including cost and conveyance of all materials to site and handling charges, leveling, compacting, curing etc. complete as per standard specifications for foundation. | 2.93 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
3 | Random Rubble stone masonry in cement mortar 1:5 for foundation and basement including using bond stone, curing and finishing etc complete complying with standard specification | 24.57 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
4 | Brick work in CM 1:5 (one cement & five sand) using country bricks Grount Chamber Burnt Size of (9 x 4 1/2" x 3") including finishing, curing,etc., complete complying with standard specification | 15.09 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
5 | Plastering with CM 1:5, 12mm thick including cost and conveyance of all materials to site and labour charges etc. complete as per standard specifications | 137.26 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
6 | Supply, delivery and fixing of M.S gate 3 x 1.80m double leaf including painting two coats with ready mixed paint of approved quality and colour for new iron works etc. over one coat of priming coat etc., complete - 30 kg/sqm | 162 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
7 | Colour washing two coats over one coat of white washing using good quality of shell lime including compacting, complying with the standard specification. | 137.26 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
8 | Refilling the trenches with excavated soil or earth (other than sand) including compacting, complying with the standard specification. | 7.02 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
1 | No.5 Proposed Construction of Pump house 10.00mx12.00mx5.00m pumping machinery at Ponnankurichi Headworks
1 | PUMP HOUSE (10 x 12 x 5m) - CIVIL WORKS
1 | Earthwork excavating for foundation and depositing on sides with an initial lead of 10 m and initial lift of 2 m in trenches (Hard stiff clay, stiff black cotton, hard red earth, shales, murram gravel, stoney earth and earth mixed with small boulders and hard gravelly soil) SS 20B complete as per standard specifications and as directed by the Engineer | 52.57 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
2 | Sand Filling in the foundation and basement including complete consolidation and levelling as per standard specifications and as directed by the Engineer | 23.06 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
3 | Plain Cement concrete 1:4:8 (one cement, four sand and eight course aggregate of 40mm size hard blue granite broken stone) for levelling course for foundation including the cost of mixing, placing the concrete in position, consolidating finishing and curing etc., complete and as directed for works above 1.50m and upto 4.50m depth below ground level. | 20 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
4 | Construction of brick masonry using Country bricks in CM 1:5 in substructure / superstructure including curing etc all complete as per standard specifications and as directed by the Engineer.
1 | Below Ground level | 29.3 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
2 | Above Ground Level | 68 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
5 | Construction of brick masonry using Country bricks in CM 1:5 in superstructure above 4.5 from ground including curing etc all complete as per standard specifications and as directed by the Engineer. | 71.32 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
6 | Providing and laying RCC M30 using coarse aggregate 20mm nominal size (crusher broken) obtained from approved quarry including mechanical mixing, vibrating, compaction, finishing, curing but excluding the cost of shuttering and reinforcement etc., complete as per standard specifications and as directed by the Engineer.
1 | Up to 4.5 m height | 6.37 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
2 | Above 4.5 m height | 25.4 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
7 | Providing & fabricating steel reinforcement for RCC works including decoiling, cutting, hooking, bending, cranking fabricating to required shape placing in position and binding complete including cost of binding wire, all RCC works like foundations, roof | 2542 | 1 Kg(One Kilo gram) |  | 0 | Rupees only | 0
8 | Centering for soffits for RCC slabs of plane surfaces including strutting 3 m height using Ms sheets of size 90x60cm and BG 10 Gauge with lintels Ms angles of size 25x25x3mm laid over silver Oak (Country wood) joists of size 10x6.5cm ( Spaced about 90 cm
1 | Upto 3.5 m ht | 47.83 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
2 | At 5.00m ht | 156.33 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
9 | Inside plastering in CM 1:4, 12 mm thick including necessary scaffolding, water the surface etc all complete as per standard specification and as directed by the Engineer. | 631 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
10 | Outside plastering in CM 1:4, 20 mm thick including necessary scaffolding, watering the surface etc all complete as per standard specification and as directed by the Engineer. | 145 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
11 | Refilling the excavated trenches using excavated earth including complete consolidation and leveling as per standard specifications and as directed by the Engineer | 16.19 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
12 | Transportation of excess earth from the pump room, including labour charges and transport to 1 km from the site as per standard specifications and as directed by the Engineer | 36.38 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
13 | Granolithic flooring 25mm thick with CC 1:2:4 mix using 10 to 12 mm HBG metal including all labour charges etc complete | 112.4 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
14 | Supplying and fixing CW frames for Doors, windows and ventilators and anyother similar joinery works including labour charges for rod and putup in position and also for fixing holdfastes in frames and masonary etc., complete in all floors | 0.51 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
15 | Providing and fixing in position Country wood panelled doors and windows as specified below and as per standard specifications and as directed by the Engineer | 24.7 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
16 | White washing with 2 coats - Inside & outside and as per standard specifications and as directed by the Engineer | 776 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
17 | Colour washing with 2 coats - same as white washing and as per standard specifications and as directed by the Engineer | 664 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
18 | Painting of panelled doors and windows with 2 coats of enamel paint inlcuding a coat of primer of specified brand etc all complete as per standard specifications and as directed by the Engineer. | 55.57 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
19 | Weathering course with brick jelly 20mm gauge in pure slacked lime over RCC roof slab in the proportion of 32:12 ½ (No sand to be used) well beaten with wooden beaters to the required depth of 80mm thick and giving required slope and thickness to roof as required, etc., complete. | 9 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
20 | Terrace flooring with 2 courses of flat tiles 20 x 20 x 2 cm using Cement Mortar 1:2 mixing with water proof compound 2% by weight of cement and pointed with same mortar | 127 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
21 | Supplying and erecting pull and push type rolling shutter with ISI make of approved size and section using 18 GI sheet. The shutter shall be painted with one coat of red oxide primer and the rate is inclusive of hood covers, transportation charges etc., | 6 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
22 | Painting 2 coats over iron works synthetic enamel paint inlcuding a coat of primer of specified brand etc all complete as per standard specifications and as directed by the Engineer. | 15 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
23 | Cable Trench
24 | Earthwork excavation in all soils for foundation except hard rock that requires blasting with initial lead of 10m and lift of 2m etc. complete as per standard specifications complete | 13.46 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
25 | Providing PCC 1:4:8, using 40mm ISS HBG metal including cost and conveyance of all materials to site and handling charges, leveling, compacting, curing etc. complete as per standard specifications for foundation. | 4.9 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
26 | Brick work in CM 1:5 (one cement & five sand) using country bricks Grount Chamber Burnt Size of (9 x 4 1/2" x 3") including finishing, curing,etc., complete complying with standard specification | 2.24 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
27 | Plastering with CM 1:4, 12mm thick including cost and conveyance of all materials to site and labour charges etc. complete as per standard specifications | 20.4 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
28 | Supplying & fabrication &placing in position of RCC pre cast slab of 50mm (2") the including cost and conveyance of all materials to site and labour charges etc. complete as per standard specifications | 14.28 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
29 | Providing & fabricating steel reinforcement for RCC works including decoiling, cutting, hooking, bending, cranking fabricating to required shape placing in position and binding complete including cost of binding wire, all RCC works like foundations, roof for cover slab | 53.55 | 1 Kg(One Kilo gram) |  | 0 | Rupees only | 0
30 | Ramp for Rolling shutter Earthwork excavation in all soils for foundation except hard rock that requires blasting with initial lead of 10m and lift of 2m etc. complete as per standard specifications complete | 1.27 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
31 | Providing PCC 1:4:8, using 40mm ISS HBG metal including cost and conveyance of all materials to site and handling charges, leveling, compacting, curing etc. complete as per standard specifications for foundation. | 0.32 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
32 | Brick work in CM 1:5 (one cement & five sand) using country bricks Grount Chamber Burnt Size of (9 x 4 1/2" x 3") including finishing, curing,etc., complete complying with standard specification | 0.41 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
33 | Brick work in CM 1:5 (one cement & five sand) using country bricks Grount Chamber Burnt Size of (9 x 4 1/2" x 3") including finishing, curing,etc., complete complying with standard specification | 1.08 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
34 | Refilling the trenches with excavated soil or earth (other than sand) including compacting, complying with the standard specification. | 1.08 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
35 | Providing PCC 1:4:8, using 40mm ISS HBG metal including cost and conveyance of all materials to site and handling charges, leveling, compacting, curing etc. complete as per standard specifications for foundation. | 0.62 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
36 | Flooring with granolithic finish with CC 1:2:4 using 10-12mm chips including cost and conveyance of all materials to site and handling charges, leveling, compacting, curing etc. complete as per standard specifications | 10.08 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
37 | Masonry support blocks for pipes Brick work in CM 1:5 (one cement & five sand) using country bricks Grount Chamber Burnt Size of (9 x 4 1/2" x 3") including finishing, curing,etc., complete complying with standard specification | 1.26 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
38 | Plastering with CM 1:4, 12mm thick including cost and conveyance of all materials to site and labour charges etc. complete as per standard specifications | 10.46 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
1 | Bill No.6 Providing Internal Water Distribution Syestem
1 | Earthwork excavation and depositing on bank with an initial lead of 10m and initial lift of 2m in trenches in Sand, silt or other loose soil, wet sand or silt not under water, light black cotton soil, sandy loam and ordinary soilall complete as per standard specifications and as directed by the Engineer.
1 | 100mm diameter DI | 35917 | 1m (One metre) |  | 0 | Rupees only | 0
2 | 150mm diameter DI | 11364 | 1m (One metre) |  | 0 | Rupees only | 0
3 | 200mm diameter DI | 3944 | 1m (One metre) |  | 0 | Rupees only | 0
4 | 250mm diameter DI | 510 | 1m (One metre) |  | 0 | Rupees only | 0
2 | Supplying and conveying to site, the following sizes of DI pipes of class K7 confirming to IS:8329-2000 as specified in Technical specifications in standard lengths including labour charges for loading, unloading and stacking at site etc. complete as per standard specifications and as directed by the Engineer.
1 | 100mm diameter DI | 35917 | 1m (One metre) |  | 0 | Rupees only | 0
2 | 150mm diameter DI | 11364 | 1m (One metre) |  | 0 | Rupees only | 0
3 | 200mm diameter DI | 3944 | 1m (One metre) |  | 0 | Rupees only | 0
4 | 250mm diameter DI | 510 | 1m (One metre) |  | 0 | Rupees only | 0
3 | Lowering of DI Pipes (K7 Class) and specials carefully into the trench and laying to proper grade and alignment including labour charges, incidental and operational charges etc complete as per standard specifications and as directed by the Departmental Engineer
1 | 100mm diameter DI | 35917 | 1m (One metre) |  | 0 | Rupees only | 0
2 | 150mm diameter DI | 11364 | 1m (One metre) |  | 0 | Rupees only | 0
3 | 200mm diameter DI | 3944 | 1m (One metre) |  | 0 | Rupees only | 0
4 | 250mm diameter DI | 510 | 1m (One metre) |  | 0 | Rupees only | 0
4 | Cutting of DI pipes and specials true to axis and filing smoothly and finishing the ends complete, with / without water in the pipe including labour charges, incidental and operational charges etc complete as per standard specifications and as directed by the Departmental Engineer
1 | 100mm diameter DI | 359 | 1No (One Number) |  | 0 | Rupees only | 0
2 | 150mm diameter DI | 114 | 1No (One Number) |  | 0 | Rupees only | 0
3 | 200mm diameter DI | 39 | 1No (One Number) |  | 0 | Rupees only | 0
4 | 250mm diameter DI | 5 | 1No (One Number) |  | 0 | Rupees only | 0
5 | Jointing the DI pipes and specials with Socket & Spigot ends (tyton rubber joints) including cost of jointing materials such as rubber gaskets and testing to the required pressure including conveyance of water for filling during testing, labour charges and all other incidental charges etc complete as per standard specifications and as directed by the Departmental Engineer
1 | 100mm diameter DI | 7183 | 1No (One Number) |  | 0 | Rupees only | 0
2 | 150mm diameter DI | 2273 | 1No (One Number) |  | 0 | Rupees only | 0
3 | 200mm diameter DI | 789 | 1No (One Number) |  | 0 | Rupees only | 0
4 | 250mm diameter DI | 102 | 1No (One Number) |  | 0 | Rupees only | 0
6 | Labour for cutting open BT or Macadam roads for laying water distribution lines etc complete as per standard specifications and as directed by the Engineer.
1 | For Mains | 413.9 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
7 | Supplying and Conveying to site, the following CI Double Flanged Sluice Valves (PN 1.0) with cap of following sizes confirming to IS:14846, including flanged tail pieces and other specials as required, loading, unloading, transportation charges & stacking at site etc complete as per standard specifications and as directed by the Engineer.
1 | 80 mm diameter | 2 | 1 Each (one each) |  | 0 | Rupees only | 0
2 | 100 mm diameter | 2 | 1 Each (one each) |  | 0 | Rupees only | 0
3 | 125 mm diameter | 2 | 1 Each (one each) |  | 0 | Rupees only | 0
4 | 150mm diameter | 6 | 1 Each (one each) |  | 0 | Rupees only | 0
5 | 200 mm diameter | 1 | 1 Each (one each) |  | 0 | Rupees only | 0
6 | 250 mm diameter | 1 | 1 Each (one each) |  | 0 | Rupees only | 0
8 | Supplying and Conveying to site, for 100mm scour valve, (PN 1.0) of following sizes confirming to IS:14846 including CI flanged tail pieces and other specials as required, loading, unloading, transportation charges and stacking, including CI bends and pipe for discharge above ground level etc complete as per standard specifications and as directed by the Engineer.
1 | 100 mm diameter | 6 | 1 Each (one each) |  | 0 | Rupees only | 0
9 | Constructing masonry chamber of inside dimensions as mentioned below with Class 1 designation, brick work in cement mortar 1:5 (1 cement : 5 coarse sand) for sluice valve, with CI Surface box 100mm top diameter, 160mm bottom diameter and 180mm deep (inside) with chained lid and top RCC Pre-cast slab 1:2:4 (1 cement : 2 coarse sand : 4 graded stone aggregate of 20mm nominal size) with necessary earth work excavation including refilling the sides of foundation, foundation concrete 1:3:6 (1 cement : 3 coarse sand : 6 grade stone aggregate 20mm nominal size) and inside plastering with cement mortar 1:5 (1 cement : 5 coarse sand) 12mm thick finished with a floating coat of neat cement, complete as per standard design and as shown in the drawings.
1 | 750x750x1200mm clear inside dimensions | 15 | 1 Each (one each) |  | 0 | Rupees only | 0
2 | 900x900x1500mm clear inside dimensions | 5 | 1 Each (one each) |  | 0 | Rupees only | 0
10 | Supplying and conveying of required specials like Tees, Bends, Reducers, End caps etc for all pipelines including transportation charges, etc complete as per standard specifications and as directed by the Engineer 10% of pipe rates | 59923 | 1kg(One kilo gram ) |  | 0 | Rupees only | 0
11 | Refilling trenches with excavated soil in layers not exceeding 20 cm in depth, ramming and consolidation of each layer, watering etc. all complete as per standard specifications and as directed by the Engineer
1 | 100mm diameter DI | 35917 | 1 Each (one each) |  | 0 | Rupees only | 0
2 | 150mm diameter DI | 11364 | 1 Each (one each) |  | 0 | Rupees only | 0
3 | 200mm diameter DI | 3944 | 1 Each (one each) |  | 0 | Rupees only | 0
4 | 250mm diameter DI | 510 | 1 Each (one each) |  | 0 | Rupees only | 0
12 | ROAD RESTORATION : Earthwork excavation and depositing on bank with an initial lead of 10m and initial lift of 2m in trenches in Sand, silt or other loose soil, wet sand or silt not under water, light black cotton soil, sandy loam and ordinary soilall complete as per standard specifications and as directed by the Engineer. for road restoration work | 1179 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
13 | Supplying and Filling for river sand including complete consolidation and levelling as per standard specifications and as directed by the Engineer | 393 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
14 | Plain Cement concrete 1:4:8 (one cement, four sand and eight course aggregate of 40mm size hard blue granite broken stone) for levelling course for foundation including the cost of mixing, placing the concrete in position, consolidating finishing and curing etc., complete and as directed for works above 1.50m and upto 4.50m depth below ground level. | 393 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
15 | Plain Cement concrete 1:2:4 (one cement, two sand and four course aggregate of 20mm size hard blue granite broken stone) for levelling course for foundation including the cost of mixing, placing the concrete in position, consolidating finishing and curing etc., complete and as directed for works above 1.50m and upto 4.50m depth below ground level. | 393 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
16 | Copnveyance the excavated earth up to 2 km lead including complete consolidation and leveling as per standard specifications and as directed by the Engineer | 1179 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
1 | N0.7 Proposed Construction of Compund wall with Gate and Chain Link Fencing for Head works at Ponnankurichi Headworks
1 | Earthwork excavating for foundation and depositing on sides with an initial lead of 10 m and initial lift of 2 m in trenches (Hard stiff clay, stiff black cotton, hard red earth, shales, murram gravel, stoney earth and earth mixed with small boulders and hard gravelly soil) SS 20B complete as per standard specifications and as directed by the Engineer | 427.5 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
2 | Providing PCC 1:4:8, using 40 mm ISS HBG metal including cost and conveyance of all materials to site and handling charges, leveling, compacting, curing etc. complete as per standard specifications for foundation. | 42.75 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
3 | Random Rubble stone masonry in cement mortar 1:5 for foundation and basement including using bond stone, curing and finishing etc complete complying with standard specification | 359.1 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
4 | Brick work in CM 1:5 (one cement & five sand) using country bricks Kiln Burnt Size of (8 3/4" x 4 1/4" x 2 3/4") including finishing, curing,etc., complete complying with standard specification | 235.59 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
5 | Plastering with CM 1:5, 12 mm thick including cost and conveyance of all materials to site and labour charges etc. complete as per standard specifications | 2151.38 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
6 | Supply, delivery and fixing of M.S gate 3 x 1.5 m double leaf including painting two coats with ready mixed paint of approved quality and colour for new iron works etc. over one coat of priming coat etc., complete - 50 kg/sqm Cost of materials | 480 | 1kg(One kilo gram only) |  | 0 | Rupees only | 0
7 | White Washing two coats over one coat of white washing using good quality of shell lime etc all complete as per standard specification and as directed by the Engineer. | 2151.38 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
8 | Colour washing two coats over one coat of white washing using good quality of shell lime etc all complete as per standard specification and as directed by the Engineer. | 2151.38 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
9 | Refilling the trenches with excavated soil/earth (other than sand) including compacting, complying with the standard specification. | 102.6 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
1 | No.8 Proposed Construction of Estimate for Twin Type Electrician Quarters at Ponnankurichi Headworks
1 | Earthwork excavation for foundation & depositing on bank with an initial lead of 10m & lift of 2m for depths in hard stiff clay, stiff black cotton, hard red earth mixed with small sized boulders & hard gravely soil including dewatering of water etc., as directed by Engineer. | 85.74 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
2 | Plain Cement Concrete 1:4:8using 40mm gauge hard broken stone jelly for plain cement concrete works including laying in layers of not more than 15cm thick including ramming, curing etc, complete as per standard specifications | 13.7 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
3 | Country brick work (83/4 x 4 1/4 x2 3/4") in Cement Mortar 1:5 for 23cm thick wall including curing etc all complete (Upto Basement) | 31.38 | 1 m3 (One Cubic metre) |  |  | Rupees only | 0
4 | Country brick work (83/4 x 4 1/4 x2 3/4") in Cement Mortar 1:5 for 23cm thick wall including curing etc all complete (Above Basement)
1 | Upto 4.50m from GL | 54.4 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
5 | Plastering with cement mortar 1:5 for 12mm thick including curing etc complete
1 | Inside Plastering | 383.81 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
2 | Outside plastering | 121.89 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
6 | Special Ceiling Plastering for RCC slabs, and beams in CM 1:3 - 10mm thick including hacking and curing etc. complete | 74.38 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
7 | Providing form work with centering for soffits of reinforced cement concrete slabs or plain surfaces including strutting upto 3m high. Strutting to centerings of reinforced cement concrete slabs or plain surface for every additional 1m high or part thereof but not less than 30cm over the initial 3m high | 129.66 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
8 | Providing & laying in position machine batched, machine mixed and machine vibrated design mix cement concrete of M30 grade for Reinforced Cement Concrete structural elements under controlled water cement ratio with plasticier using 20mm and down graded machine broken granite stone jelly excluding the cost of centering and shuttering & reinforcement but including curing, fixing, etc as per standard specification and as directed by the Board officers complete | 15.84 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
9 | Supplying, fabricating and laying in position MS rounds or RTS rods for RCC works including cost of reinforcement, binding wire, cutting, bending, cranking and tying in position with binding wire assembly, etc. | 1584 | 1kg(One kilo gram only) |  | 0 | Rupees only | 0
10 | Providing Weathering Course with brick jelly and lime including curing etc., complete. | 5.46 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
11 | Terrace flooring with two course of flat tiles 20 x 20 x 2 cm using cement mortar 1:2 mixed with water proof compound 2% by weight of cement and pointed with same mortar | 67.47 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
12 | Granolithic flooring 25mm thick with CC 1:2:4 mix using 10 to 12 mm HBG metal including all labour charges etc complete | 71.24 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
13 | Supplying and filling sand for foundations and basement including watering consolidating ramming, etc., complete | 31.63 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
14 | Refilling with excavated soils (other than sand) complying with standard specifications and as directed by the Engineer. | 46.04 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
15 | Supplying and fixing of RCC Jalli etc complete as per standard specifications and as directed by the Engineer | 1.08 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
16 | Supplying and fixing of country wood frames for Doors & Windows including labour charges for wrought and put up in position and for fixing hold fast in frames etc complete | 1.07 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
17 | Supplying and fixing of country wood fully panelled door shutters including cost of furniture fits and all labour charges etc complete | 24.49 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
18 | Supplying and fixing of country wood shutters for windows including cost of furniture fits and all labour charges etc complete | 8.28 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
19 | White washing with 2 coats - Inside & outside etc complete as per standard specifications and as directed by the Departmental Engineer | 505.71 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
20 | Colour washing with 2 coats - same as white washing etc complete as per standard specifications and as directed by the Departmental Engineer | 505.71 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
21 | Painting new wood work with two coats of synthetic enamal paint over a priming coat including cost of primer etc. complete as directed
1 | Frames | 34.39 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
2 | Shutters | 32.77 | 1 m2(One Square metre) |  | 0 | Rupees only | 0
1 | No. 9 Providing Water supply HSC with meter at Kayalpattanam municipality Area.
1 | Earth work excavation in sandy soil for foundation with initial lead and lift including all cost and conveyance etc., complete. SS20B | 15510.38 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
2 | Labour for cutting open road for laying water main
1 | a) BT Road (or) macadam road | 1578.49 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
2 | b) Concrete road | 2127.53 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
3 | Supply of following MDPE /PVC/GI Pipes and specials of standard quality directed to departmental officer
1 | 1/2'' MDPE pipe | 68630 | 1Rm (one running metre) |  | 0 | Rupees only | 0
2 | 1/2'' GI Pipe | 13726 | 1Rm (one running metre) |  | 0 | Rupees only | 0
3 | 11/4'' GI pipe | 10294.5 | 1Rm (one running metre) |  | 0 | Rupees only | 0
4 | saddle piece MS | 3431.5 | 1 No(One Each) |  | 0 | Rupees only | 0
5 | saddle piece PVC | 6863 | 1 No(One Each) |  | 0 | Rupees only | 0
6 | GM Ferrule | 6863 | 1 No(One Each) |  | 0 | Rupees only | 0
7 | 1/2''x3/8'' GI reducer | 13726 | 1 No(One Each) |  | 0 | Rupees only | 0
8 | 1/2'' GI dia.MTA | 34315 | 1 No(One Each) |  | 0 | Rupees only | 0
9 | 1/2'' GI elbow | 6863 | 1 No(One Each) |  | 0 | Rupees only | 0
10 | 1/2'' dia Tap | 6863 | 1 No(One Each) |  | 0 | Rupees only | 0
11 | 1/2'' dia water meter | 6863 | 1 No(One Each) |  | 0 | Rupees only | 0
12 | Ferrule cover | 6863 | 1 No(One Each) |  | 0 | Rupees only | 0
13 | 1/2'' Dia GI coupling | 6863 | 1 No(One Each) |  | 0 | Rupees only | 0
4 | Labour for cutting threading and fixing of ferrule
1 | 10mm dia | 6863 | 1 No(One Each) |  | 0 | Rupees only | 0
2 | Cutting of 1/2'' dia GI pipe | 20589 | 1 No(One Each) |  | 0 | Rupees only | 0
3 | Threading of 1/2'' GI dia | 41178 | 1 No(One Each) |  | 0 | Rupees only | 0
4 | Laying of 1/2'' dia MDPE pipe | 68630 | 1Rm (one running metre) |  | 0 | Rupees only | 0
5 | Laying of 1/2'' dia GI pipe | 10294.5 | 1Rm (one running metre) |  | 0 | Rupees only | 0
5 | Refilling for excavated earth including all cost and conveyance etc.complete. | 15510.38 | 1 m3 (One Cubic metre) |  | 0 | Rupees only | 0
Total in Figures |  | 0
Total in Words |  | Rupees only
Note on F7: Rate in Figures: Please enter the Rate in Figures as Rupees and Paise only

## Macros
Please Enable Macros to View BoQ information